## Slide 1
factory:intake
factory:spec-ready
factory:deployed
CORPORATE TRAINING PROGRAM · 20 HOURS · 5 HALF-DAYS
AI-Enabled Project & Delivery Management
Generative AI, predictive analytics and automation for experienced Project and Delivery Managers — with the Software Factory, an agent-driven delivery pipeline, as the running case.
GenAI People · Jerry Kurian · genaipeople.com
Prepared for Gynosis Information Technology Pvt. Ltd. · Client: UST
Notes: Opening: this program is built for PMs who already run delivery well and need to run it with AI — both using AI in their own work and governing delivery where agents do most of the work.

## Slide 2
WHY THIS PROGRAM
The Project Manager's job is changing — twice
First shift: AI in the PM's own work. Charters, estimates, risk registers, status reports and stakeholder updates are now drafted in minutes. The skill moves from writing to reviewing.
Second shift: AI doing the delivery. Agents now spec, plan, design, implement, review and test. The PM stops coordinating hand-offs and starts holding gates.
What does not change. Scope, trade-offs, accountability, relationships, and the decision to ship. These get more valuable, not less.
The program teaches both halves, with hands-on labs every day and a real agent-driven pipeline on Days 4 and 5.
Assistant
Drafts for you. You paste context in, you copy the output out. Day 1.
Copilot
Works inside your tools — tracker, chat, spreadsheet, IDE. Days 2 and 3.
Agent
Does the work end to end. You approve at gates. Days 4 and 5.
AI-Enabled Project & Delivery Management · GenAI People
2

## Slide 3
PROGRAM AT A GLANCE
Five half-days, one running case
1
4 h
GenAI for the PM
Foundations · forecasting · risk
Intro to GenAI in PM
Forecasting & risk
Lab: plan + forecast
2
4 h
Automation & reporting
Workflows · status · comms
AI automation
AI reporting
Lab: automated status
3
4 h
Tools & integration
Landscape · integration · monitoring
Modern PM tools
Collaboration tools
Monitoring
Lab: tool integration
4
4 h
AI-driven delivery
The Software Factory operating model
Future of PM
Delivery best practices
Managing Gen AI projects
Lab: run an epic
5
4 h
Capstone & certification
Case study · capstone · 30-60-90
Case study
Capstone (teams)
Conclusion & certificate
Every day: three 50-minute teaching-and-demo blocks, one 60–90-minute lab, a closing round. Every module ties back to the Software Factory so the concepts are seen running, not just described.
AI-Enabled Project & Delivery Management · GenAI People
3

## Slide 4
AUDIENCE AND FORMAT
Built for senior delivery practitioners
20 h
five half-days of 4–4.5 hours, online, recorded
8
hands-on labs, one every half-day or more
1
capstone: a full AI-enabled delivery plan, presented
12–20
participants per batch; capstone teams of 3–4
Who it is for
Career Grade 4–6 Project and Delivery Managers
12–18 years total experience, 5–6 in project / delivery management
Running agile or hybrid delivery with Jira, Azure DevOps or GitHub
No coding required — labs are browser, spreadsheet and guided templates
How it is taught
Concept → live demo → lab on participants' own data or a sandbox
Sandbox GitHub organisation with the Software Factory pre-installed
Participants sit in the approver seats on Days 4–5 and open real gates
Assessment: capstone 60% + scenario quiz 40% → certificate of completion
AI-Enabled Project & Delivery Management · GenAI People
4

## Slide 5
BUSINESS OUTCOMES
Every expected business outcome has a module and a proof
Expected business outcome | Where it is built | Evidence at the end
Improved project delivery predictability | Day 1 forecasting · Day 4 small batches, staging first, release gating | P50 / P85 forecast on real data; sequenced release plan
Faster and more accurate project reporting | Day 2 reporting from the system of record · Day 3 monitoring | A working automated status report posted to Teams / Slack
Reduced risk exposure through AI-driven forecasting | Day 1 risk mining and early-warning signals · Day 4 independent review, gates | AI-mined risk register with exposure and signals
Increased productivity through workflow automation | Day 2 automation · Day 3 integration · Day 4 agents doing the work | Automation built in the lab; an epic run end-to-end by agents
Better resource utilisation and governance | Day 3 flow metrics · Day 4 gates, approvers, guardrails, model routing | Governance design in the capstone
Readiness to manage AI-driven business initiatives | Day 4 managing Gen AI projects · Day 5 capstone | Capstone delivery plan and personal 30-60-90 plan
AI-Enabled Project & Delivery Management · GenAI People
5

## Slide 6
AN AGENT-DRIVEN DELIVERY PIPELINE · OPEN SOURCE, MIT
The running case: the Software Factory
A plain GitHub issue goes in. A specced, planned, designed, implemented, reviewed, tested and released change comes out — with human approval gates, and no ability for an agent to put anything on main.
scrum
release plan
intake
proposal + specs
planner
tasks.md
architect
design.md
dispatch
ready tasks
implementer
PR per task
reviewer
line review
qa
tests green
release
staging → main
ops
verify, archive
Human gates
G0
release scope
G1
spec
G2
design
GS
to staging
G3
to production
Everything between the gates runs unattended. Only GS and G3 can never be delegated: they are the moments something leaves the factory's own branches.
Why it is the running case: the client's six outcomes — predictability, reporting, risk, automation, governance, AI readiness — are exactly what a factory-style pipeline forces you to design for. Participants see every concept of the program running on a real repository, and sit in the approver seats themselves.
AI-Enabled Project & Delivery Management · GenAI People
6
Notes: Built by GenAI People. github.com/genai-jerry/claude-software-factory. Ten roles, five gates. Emphasise: the orchestrator is not an AI — it is a routing job that reads labels. Any human can take over any stage by setting the next label.

## Slide 7
THE FACTORY'S DESIGN PRINCIPLES — AND WHAT A PM TAKES FROM THEM
Two foundations, one rule
GitHub is the state machine
Milestones are releases; issues, sub-issues and factory:* labels encode where every piece of work is. A label change is what wakes an agent.
For the PM: reporting becomes a query, not a meeting. Flow metrics come for free. Any human can take over any stage by moving the label.
OpenSpec is the content
What is being built — proposal, WHEN/THEN scenarios, technical design, task checklist — lives in the repo as plain Markdown, versioned with the code.
For the PM: the artifacts you review at a gate are short documents, not transcripts. Requirements, plan and design are one folder, one history.
Issues carry state plus a link — never spec content
Agents read requirements from the change folder, never from the issue body. That is what stops the two sources of truth from drifting.
For the PM: the single most common cause of delivery failure — the ticket says one thing, the document another — is designed out.
AI-Enabled Project & Delivery Management · GenAI People
7

## Slide 8
DAY 1 AGENDA · 4 HOURS
Day 1 — Generative AI for the project manager
0:00 – 1:00
Introduction to Generative AI in PM LLMs for PMs · assistant / copilot / agent · prompting patterns
1:00 – 1:10
Break
1:10 – 2:25
AI-driven forecasting and risk management Throughput, Monte Carlo, risk mining, early-warning signals
2:25 – 2:35
Break
2:35 – 3:50
Hands-on: from brief to plan; forecast Lab 1A charter / WBS / risks · Lab 1B Monte Carlo
3:50 – 4:00
Closing round
Client ToC modules covered
Introduction to Generative AI in Project Management
AI-Driven Project Forecasting and Risk Management
Hands-On Exercise
Software Factory thread
The Intake Analyst: an agent that stops and asks (factory:blocked) instead of inventing requirements
The Scrum Master: release scope, sequencing, risks and a GO / NO-GO on the whole milestone before anything starts
AI-Enabled Project & Delivery Management · GenAI People
8

## Slide 9
DAY 1 · MODULE 1.1 · AND WHERE IT DOES NOT
Where Generative AI fits in the PM lifecycle
Initiate
Charter and business case drafts
Stakeholder map
Assumption and question lists
Assistant
Plan
WBS, RACI, schedule skeleton
Estimate ranges with rationale
Requirements → acceptance scenarios
Assistant → Agent
Execute
Meeting → decisions and actions
Change-request summaries
Agents implementing tasks
Copilot → Agent
Monitor
Status from the system of record
Forecasts and risk signals
Attention queue: what needs me
Copilot
Close
Lessons learned from the record
Archive specs, decisions
Benefits tracking narrative
Assistant
Where it does not fit: deciding scope, negotiating trade-offs, owning the relationship, and saying yes or no at a gate. The prompting rule that matters most in delivery: ask the model for its questions and assumptions before its answer.
AI-Enabled Project & Delivery Management · GenAI People
9

## Slide 10
DAY 1 · MODULE 1.2 · PREDICTIVE ANALYTICS
Forecasting: from a date to a probability
Chart: Monte Carlo — 10,000 runs on 12 weeks of throughput
| W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
Simulations reaching done (%) | 2 | 7 | 15 | 22 | 21 | 15 | 10 | 5 | 3
P50 · week 12
P85 · week 14
A sponsor asked for week 11. The honest answer is 24% — and the model can say why.
Count things, not points. Throughput and cycle time forecast better than estimates, and need no re-estimation.
Simulate, then explain. Monte Carlo in Excel or a guided notebook gives P50 / P85; the LLM turns it into the sponsor conversation.
Stress-test the inputs. Ask the model for the scenarios that would move the P85 by two weeks — scope churn, WIP, blocked ageing.
Factory tie-in. Because every stage is a label with a timestamp, the factory produces per-stage cycle-time data by itself. Forecasting an epic is a query.
AI-Enabled Project & Delivery Management · GenAI People
10
Notes: Chart values are illustrative. In the lab, participants use a supplied 12-week throughput dataset or their own Jira/ADO export.

## Slide 11
DAY 1 · MODULE 1.2 · RISK
AI-driven risk management: mine it, classify it, watch for it
Three moves
Mine. Risks hide in tickets, retros, incident logs and meeting transcripts. An LLM reads all of it and proposes a register with sources cited.
Classify. Probability × impact is still the model; the AI drafts, the PM decides. Pre-mortems generate the risks nobody wants to say aloud.
Watch. Early-warning signals from the system of record: blocked ageing, review-queue depth, re-open rate, scope churn, cycle-time drift. Automate the watch; escalate on threshold.
Factory tie-in. The Scrum Master (right) does the first two moves on a whole release before anything starts; the state labels give you the third for free.
factory:release-ready
Release plan — release(3): Policy servicing Q4
Posted by the Scrum Master role after reading every issue in the milestone
Issue | Intent | Seq | Concern
#41 | Renewal reminders via WhatsApp | 1 | —
#42 | Premium recalculation API | 2 | schema first
#43 | Agent dashboard | 3 | depends on #42
#44 | Bulk import | — | oversized: split
#45 | Fix date format | — | fast-track
Risks 1. #42 has no owner for the rate table (ask: actuarial). 2. #43 and an in-flight change overlap on the dashboard module. Verdict GO once #44 is split and #45 leaves the milestone.
AI release planning on the set, not the item: duplicates, sequencing, size and under-specification are caught before a single agent starts. Gate G0 is the human's — or, by config, the agent's own GO.
AI-Enabled Project & Delivery Management · GenAI People
11

## Slide 12
DAY 1 · HANDS-ON EXERCISE
Lab 1: from brief to plan, then from data to a date
1A · Brief → charter, WBS, RACI, risks
Take the supplied one-page product brief
Ask the model for its questions and assumptions first
Generate charter, WBS, RACI and a risk register
Run a structured review pass: what is wrong, what is missing, what is invented
Mark up corrections side by side with the AI draft
1B · Throughput → P50 / P85
Load the 12-week throughput dataset (or your own tracker export)
Build the Monte Carlo in Excel or the guided notebook
Read the P50 and P85 dates; try a WIP-limit scenario
Have the LLM draft the sponsor explanation and the two scenarios that move the date
Deliverable A marked-up AI-drafted plan with the PM's corrections, and a probabilistic forecast with a sponsor-ready explanation.
Closing round
What changed in the plan once you asked the model for its questions first?
Which date would you have committed to before today, and which will you commit to now?
AI-Enabled Project & Delivery Management · GenAI People
12

## Slide 13
DAY 2 AGENDA · 4 HOURS
Day 2 — AI for project automation and reporting
0:00 – 1:00
Using AI for project automation Triggers, workflow tools, the LLM step, human-in-the-loop design
1:00 – 1:10
Break
1:10 – 2:10
AI-driven reporting and stakeholder communication Reports from the system of record · meeting intelligence · citations
2:10 – 2:20
Break
2:20 – 3:50
Hands-on: automated status; meeting to decisions Lab 2A weekly status to Teams / Slack · Lab 2B decision log
3:50 – 4:00
Closing round
Client ToC modules covered
Using AI for Project Automation and Reporting
Hands-On Exercise
Software Factory thread
The label state machine: one state per issue, labels trigger agents, agent comments never self-trigger
Every run ends by saying what is expected of the next actor
The Factory Console: a lens, never a second source of truth — attention queue, decision log, cited Q&A
AI-Enabled Project & Delivery Management · GenAI People
13

## Slide 14
DAY 2 · MODULE 2.1
The automation stack a PM can own
Trigger
Webhook, schedule, label change, new message
Workflow
Power Automate, n8n, Zapier, GitHub Actions
LLM step
Summarise, classify, draft, extract, route
Destination
Teams, Slack, email, Confluence, the tracker
Human review
Approve, edit, or let it through by policy
May do alone
Post a status draft to a channel
Label and route new intake
Remind owners of ageing items
Extract actions from a transcript
Must draft for approval
Client-facing communications
Scope or date changes
Escalations to a sponsor
Anything that names a person's performance
Must never touch
Merging to production
Approving a gate on a human's behalf
Deleting records
Sending data outside the client's policy
AI-Enabled Project & Delivery Management · GenAI People
14
Notes: Factory tie-in: the factory's own rule set is exactly this table. Agents label, comment and open PRs; they may never merge to main, and a hook enforces it rather than a prompt.

## Slide 15
DAY 2 · MODULE 2.2 · THE LABEL STATE MACHINE AS DATA
Report from the system of record, not from people
factory:backlog
factory:intake
factory:spec-ready
factory:spec-approved
factory:planned
factory:design-ready
factory:design-approved
factory:ready
factory:in-review
factory:in-test
factory:ready-to-ship
factory:in-staging
factory:deployed
Exactly one state label per issue. Orange states wait on a human. Every transition has a timestamp, an actor and a comment — so status, cycle time, WIP and blocked ageing are queries.
Inputs
Issues, sub-issues, labels, milestones
Pull requests and reviews
CI runs and deployments
Calendar and meeting transcripts
Never: a status meeting
The LLM is the narrator, not the source
One dataset, three audiences: sponsor, steering committee, team
Each claim cites the object it came from
As-of timestamps on every number
A review step that costs less than the mistake
Meeting intelligence
Transcript → decisions, actions, new risks
Decision log kept current automatically
In the factory: decisions are posted as ordinary GitHub comments with hidden markers — readable anywhere, indexed by the Console
AI-Enabled Project & Delivery Management · GenAI People
15

## Slide 16
DAY 2 · MODULE 2.2 · THE FACTORY CONSOLE
What an AI-era PMO dashboard looks like: the attention queue
"What needs me, and why" — a lens over GitHub, never a second source of truth. Drop its tables, replay the events, and it is whole again.
Attention queue · 4 items
G1
#42 Premium recalculation API — spec PR ready
Why you: spec approver · Waiting 2 days · 2 open questions the analyst could not answer
G2
#41 Renewal reminders — design + tasks PR ready
Why you: design approver · Changed since you looked: migration plan added
!
#43 Agent dashboard — factory:blocked
Why you: epic owner · Implementer asks: which auth scope does the widget use?
GS
#38 Claims export — epic assembled and green
Why you: staging approver · 6 tasks merged in order, system tests 5/5 passed
Attention, not activity. The queue lists decisions waiting on you, each with the reason it is yours and how long it has waited.
What changed since you looked. As-proposed ⇄ as-approved diffs of the spec and design, so a re-review is minutes.
Decision log. Every gate approval is a recorded decision; every recorded decision is searchable.
Ask the Factory. Cited Q&A that answers only from the epic's own artifacts, threads, PRs and runs — with a token budget per organisation.
Lesson for any dashboard: show the person what needs them, cite the source object, and never become the place the truth lives.
AI-Enabled Project & Delivery Management · GenAI People
16

## Slide 17
DAY 2 · HANDS-ON EXERCISE
Lab 2: a status report nobody has to write
2A · Automated weekly status
Connect the sandbox repo (or your tracker export) to the workflow tool
Pull open issues, PRs, blocked items and deployments
LLM step: sponsor-grade and team-grade versions from the same data, every claim cited
Post both to a Teams / Slack channel; add a human-review branch for the sponsor version
2B · Meeting → decisions
Take a supplied 40-minute transcript
Extract decisions, actions and new risks, each with a timestamp
Post the decisions as structured comments on the epic
Compare with the human minutes: what did each miss?
Deliverable A working automated status pipeline posting to a channel, and a decision log generated from a transcript with citations.
Closing round
Which of your current reports could disappear next month?
What would you need to trust before the sponsor version goes out unreviewed?
AI-Enabled Project & Delivery Management · GenAI People
17

## Slide 18
DAY 3 AGENDA · 4 HOURS
Day 3 — Technology and tools for modern project management
0:00 – 0:50
Overview of modern PM tools Jira, ADO, GitHub, Asana, Linear, Notion, MS Project — and where the AI is
0:50 – 1:40
Integrating collaboration and communication tools Webhooks, APIs, bots, MCP · identity and permissions
1:40 – 1:50
Break
1:50 – 2:40
Advanced techniques for project monitoring Flow metrics, DORA, dashboards, anomaly detection, attention vs alerts
2:40 – 2:50
Break
2:50 – 4:00
Hands-on: tool integration Lab 3: repo → chat → LLM summary → flow dashboard
Client ToC modules covered
Overview of Modern Project Management Tools
Integrating Collaboration and Communication Tools
Advanced Techniques for Project Monitoring
Hands-On Exercise: Tool Integration
Software Factory thread
Plain GitHub objects as the whole state; OpenSpec folders as the content — vendor-neutral and resumable
The control path: event → caller stub → router → role → label moves
Approvers named in config; GitHub's own notifications do the work
AI-Enabled Project & Delivery Management · GenAI People
18

## Slide 19
DAY 3 · MODULE 3.1
The tool landscape — choose by delivery model, not feature list
Work tracking
Jira + Atlassian Intelligence / Rovo · Azure DevOps + Copilot · GitHub Projects + Copilot · Linear · Asana AI · Monday · ClickUp Brain
Knowledge and specs
Confluence · Notion AI · SharePoint + Copilot · OpenSpec change folders · ADRs and design docs as reviewable artifacts
Collaboration
Microsoft Teams + Copilot · Slack AI · meeting recorders (Teams, Zoom, Fireflies, Otter) · email as the record
Monitoring and BI
Power BI · Looker · Grafana · Jira dashboards · DORA tooling (LinearB, Jellyfish, DX) · the Factory Console
AI assistants and agents
ChatGPT · Claude · Microsoft Copilot · Claude Code · GitHub Copilot coding agent · Cursor · orchestration (GitHub Actions, LangGraph)
Automation
Power Automate · n8n · Zapier · GitHub Actions · Model Context Protocol (MCP) servers that expose tools to assistants
Three questions before any tool: where does the system of record live, what must be integrated versus merely coexist, and who is the identity every automated action runs as?
AI-Enabled Project & Delivery Management · GenAI People
19

## Slide 20
DAY 3 · MODULE 3.2 · INTEGRATION PRIMITIVES, SEEN IN THE FACTORY
How an event becomes an action: the control path
GitHub event
issue opened · label applied · comment 'Approved' · PR merged
Caller stub
~20 lines in the repo: triggers and a version pin, no logic
Router
Reads the event and the current label; names a role or replies why nothing ran
Role runs
One agent, one issue, a model chosen per stage
Visible trace
Label moved, comment posted, next actor @-mentioned. No silent green runs
Primitives every PM should know
Webhook: the tool calls you when something happens
API: you ask the tool
Bot: an identity that acts in chat
MCP: a standard way to give an AI assistant tools — your tracker, your docs, your calendar
Identity and permissions
Every automated action runs as someone
Approvals are recorded in the tool that owns the decision
In the factory, the Console posts approvals under the user's own GitHub identity — it adds zero new enforcement paths
Approvers are a config file; the pipeline assigns and @-mentions them
Avoiding notification debt
Teams / Slack for attention, email for the record, the assistant for questions
One channel per project, one thread per epic
Digest what is informational; interrupt only for decisions
Say, on the object, what is expected of the next actor
AI-Enabled Project & Delivery Management · GenAI People
20

## Slide 21
DAY 3 · MODULE 3.3
Monitoring that answers questions: flow metrics and DORA
Chart: Cycle time by stage — one epic, from the label history (days)
| intake | spec gate | plan+design | design gate | implement | review | test | staging gate | prod gate
Median days in stage | 0.3 | 2.1 | 0.4 | 1.6 | 1.2 | 0.5 | 0.6 | 1.9 | 0.8
Where did the 9.4 days go? 6.4 of them were humans at gates. The agents took 3.0. Decision latency is the new constraint.
Flow metrics
Throughput · cycle time · WIP · flow efficiency · ageing
Read together: rising WIP with flat throughput is the earliest warning you get
DORA
Deployment frequency · lead time · change-failure rate · time to restore
In the factory: factory:deployed and factory:incident are the two labels that make these a query; the Ops role's smoke and soak checks feed them
AI-Enabled Project & Delivery Management · GenAI People
21
Notes: Chart values are illustrative. Point: AI monitoring is anomaly and trend detection on top of these, and an attention queue instead of an alert firehose.

## Slide 22
DAY 3 · HANDS-ON EXERCISE
Lab 3: wire the tools together
Repo → chat → LLM → dashboard
In the sandbox GitHub organisation, connect a repository to a Teams / Slack channel
Add an LLM summarisation step on issue and PR events (what changed, who is waiting, why)
Build a small flow-metrics dashboard from the label history: cycle time by stage, WIP by state, blocked ageing
Stretch: expose the tracker to an AI assistant through MCP and ask it delivery questions in plain English
Stretch: add an anomaly rule — alert when blocked ageing exceeds two days
Deliverable A live integration from the system of record to the team's chat, with an LLM in the loop, and a dashboard that reads from the same events.
Closing round
Which one integration would you add to your current project first?
What did the LLM summary get wrong, and what would you give it to fix that?
AI-Enabled Project & Delivery Management · GenAI People
22

## Slide 23
DAY 4 AGENDA · 4 HOURS · THE SOFTWARE FACTORY OPERATING MODEL
Day 4 — Managing AI-driven delivery
0:00 – 0:45
The future of project management Managing people and agents · the PM as gatekeeper · skills that appreciate
0:45 – 1:45
Best practices for project delivery in tech projects Spec-driven · small batches · staging first · independent review · guardrails as controls
1:45 – 1:55
Break
1:55 – 2:55
Practical guide to managing Gen AI projects Non-determinism, evaluation, cost, privacy, responsible AI, model routing
2:55 – 3:05
Break
3:05 – 4:20
Hands-on: run an epic through the factory Lab 4: file it, plan the release, open G0 → G1 → G2 → GS, see what G3 asks
Client ToC modules covered
The Future of Project Management
Best Practices for Project Delivery in Tech Projects
Practical Guide to Managing Gen AI Projects
Software Factory thread
This is the day the factory is the subject, not the example
Ten roles, the state machine, five gates — and why only GS and G3 are structural
Guardrails: a hook, a deny list, a detector
Model routing: spend quality where errors compound
AI-Enabled Project & Delivery Management · GenAI People
23

## Slide 24
DAY 4 · MODULE 4.1 · THE FUTURE OF PROJECT MANAGEMENT
From managing people to managing people and agents
What gets automated
Coordination and hand-offs between stages
Status collection and first-draft reporting
First-draft artifacts: specs, plans, designs, test plans
Implementation, review and testing of well-specified work
Release assembly: dependency-ordered merges, staging checks
What stays human — and appreciates
Scope, priorities and trade-offs
Writing an unambiguous requirement
Reading a design and a test report well enough to say no
Opening the gates that put code on staging and in production
Relationships, escalation, accountability
The pipeline waits on a human, not the other way round. When agents take minutes and approvals take days, decision latency becomes the delivery constraint. The PM's operating rhythm changes from weekly status to daily gates — and the PMO's dashboard changes from activity to attention.
AI-Enabled Project & Delivery Management · GenAI People
24

## Slide 25
DAY 4 · MODULE 4.2
Ten roles, five gates: the factory pipeline in one picture
# | Stage | Role | Produces | Gate | Who opens it
0 | Release | scrum | Release plan for one milestone: scope, sequencing, risks, GO / NO-GO | G0 | release scope approver — or the agent's own GO
1 | Intake | intake | proposal.md + WHEN/THEN scenarios, opened as a PR; stops and asks if ambiguous | G1 | spec approver reviews the PR, comments 'Approved'
2 | Plan | planner | tasks.md — ≤ ~10 tasks of ≤ half a day, one PR each, mirrored into sub-issues |  | 
3 | Design | architect | design.md per repo: contracts, migrations, failure modes; reads the actual code first | G2 | design approver — plan and design are one approval
4 | Dispatch | dispatch | Marks tasks whose dependencies are merged as ready; no judgement, pure coordination |  | 
5 | Implement | implementer | Branch, tests, draft PR — exactly one task per session |  | 
6 | Review | reviewer | Independent session, different model; approve or send back |  | 
7 | Test | qa | Scenario → test mapping, suites green, test report on the PR |  | 
8 | Deploy | release | Dependency-ordered merges onto the epic branch, then integration, then promotion PRs | GS | staging approver: 'Approved' on the assembled epic
9 | Verify | ops | Health and smoke checks, soak, archive the change, close the issue | G3 | a human presses Merge on the promotion PR — never an agent
Beside the stages: a fast lane (factory:fast-track) for changes too small for the ceremony, and expedite (factory:expedite) for all of the ceremony and none of the pauses — which still stops at GS.
AI-Enabled Project & Delivery Management · GenAI People
25

## Slide 26
DAY 4 · MODULE 4.2 · BEST PRACTICES FOR PROJECT DELIVERY IN TECH PROJECTS
Delivery best practices, as the factory enforces them
Spec-driven delivery
A change is a proposal, acceptance scenarios, a design and a task list — each reviewed before the next is written.
Small batches
Tasks of at most half a day, one PR each, ordered so every intermediate merge is releasable: schema → service → consumer.
Staging first, always
Nothing reaches main that was not assembled and proven on an integration branch. Promotion PRs carry the staging evidence.
Independent review
A reviewer that never shares the implementer's context — in the factory, a different model, so the blind spots differ.
Guardrails as controls
A hook blocks the push, a deny list removes the merge tool, a detector files an incident. Not a policy document.
Release gating
A milestone is the release. Nothing starts until the whole set has been read, sequenced and approved — once.
AI-Enabled Project & Delivery Management · GenAI People
26

## Slide 27
DAY 4 · MODULE 4.2 · GUARDRAILS
Governance you can prove: controls, not instructions
1
Prevent
A pre-tool-use hook blocks any agent git push to main or master — every refspec form, force pushes, deletes. Tested like code.
2
Remove
A permission deny list removes the PR-merge tools from every agent session. Humans merge in the GitHub UI; that click is gate G3.
3
Detect
A detection workflow opens a factory:incident issue if a commit ever lands on main without a pull request, or by a PR that did not come from staging.
Plus: agent comments carry a marker so they never trigger themselves; a gate flip is checked against the approver list no matter who sends it.
What a PM takes from this
A rule an AI system 'should follow' is a wish. A rule the toolchain enforces is a control.
Ask of every AI initiative: what can it not do, and how do we know?
Detection is the third layer, not the first — and it must page a person.
Approver lists, gate evidence and decision logs are the audit trail regulators will ask for.
The same three layers apply to a chatbot, an automation, or a coding agent.
AI-Enabled Project & Delivery Management · GenAI People
27

## Slide 28
DAY 4 · MODULE 4.3 · PRACTICAL GUIDE
Managing Gen AI projects: what is actually different
Non-deterministic output
The same input gives different answers. Pass / fail testing becomes evaluation on a curated set with a threshold.
Evaluation is the schedule
Most of the time goes into the eval loop, integration and change management — not the model.
Cost is tokens
Budget per run, per stage, per organisation. Route cheap models to volume, strong models to judgement.
Drift
Prompts, models and data all move. Version them; re-run the evals on every change.
Data in the prompt
Privacy and confidentiality apply to what goes in and what comes out. Client policy decides the assistant.
Vendor dependency
Keep state and content vendor-neutral; only the execution layer should be tied to one model provider.
The Gen AI project lifecycle
Use-case triage
Data & access
Prototype
Evaluation set
Guardrails
Pilot
Monitor & route
Responsible AI in one line each: transparency (say what the AI did), human oversight (a person holds the gate), auditability (the decision log), lawfulness (EU AI Act risk tiers, India's DPDP Act, the client's own AI policy).
AI-Enabled Project & Delivery Management · GenAI People
28

## Slide 29
DAY 4 · MODULE 4.3 · COST AND QUALITY MANAGEMENT FOR AI WORK
Model routing: spend quality where errors compound
Stages | Preference chain | Why
scrum · intake · planner · architect · reviewer | Fable 5 → Opus 5 → Sonnet 5 | A wrong release scope, spec, plan or design — or a missed review defect — multiplies downstream. The model delta is cheap by comparison.
implementer · qa · release | Opus 5 → Sonnet 5 | Strong coding and testing on the volume stages, guard-railed by the merged design and the spec scenarios.
dispatch · ops | Haiku 4.5 → Sonnet 5 | Mechanical coordination and checks. Fast and cheap; nothing here needs judgement.
Preference chains, not a single model
Before launching, the pipeline probes each model with a one-token ping and uses the first the credential can reach. A plan or tier gap degrades gracefully instead of failing the run.
Budgeting an estate
Cost per role per run × runs per epic × epics per release. The Console holds a token budget per organisation for its Q&A. Ask the same of any AI vendor: what does one unit of work cost?
The PM's version of this
Use the strong model for the artifacts people will sign off on; the fast one for the drafts, summaries and reminders. Review where the error would compound.
AI-Enabled Project & Delivery Management · GenAI People
29

## Slide 30
DAY 4 · HANDS-ON EXERCISE · 75 MINUTES
Lab 4: run an epic through the factory — in the approver seats
1
File
A requirement against a milestone in the sandbox estate. It parks in factory:backlog.
2
Plan release
Comment it on the tracker. Read the Scrum Master's scope, order, risks and verdict.
3
G0
Comment 'Approved'. Every backlog issue in the milestone enters intake at once.
4
G1
Review the proposal and WHEN/THEN scenarios. Send one back with questions — see factory:blocked work.
5
G2
Read tasks.md and design.md in one PR. Approve. The Dispatcher releases the unblocked tasks.
6
Watch
Implement → review → test run unattended. Read the review and the test report as they land.
7
GS
The epic is assembled and green. Approve; the Release Manager carries it to staging and verifies.
8
G3
See what the promotion PR asks of a human, and why no agent can press that button.
Roles rotate: release-scope approver, spec approver, design approver, tester. Closing round: which of your current sign-offs are gates, and which are merely waiting?
AI-Enabled Project & Delivery Management · GenAI People
30

## Slide 31
DAY 5 AGENDA · 4 HOURS
Day 5 — Capstone, governance and certification
0:00 – 0:45
Case study discussion The four-repository estate · porting the pipeline to another runner · what applies to you
0:45 – 0:55
Break
0:55 – 2:55
Capstone project (teams of 3–4) AI-enabled delivery plan for a case-study release, six deliverables
2:55 – 3:05
Break
3:05 – 3:40
Capstone presentations and critique 10 minutes per team, scored against the outcome measures
3:40 – 4:15
Course conclusion, 30-60-90 plan, certification Recap, scenario quiz, personal adoption plan, certificate
Client ToC modules covered
Capstone Project & Case Study Discussion
Course Conclusion and Certification
Software Factory thread
The original deployment: four repositories, one pipeline — what it cost, what broke, what the gates caught
The same shape on GitHub Copilot: what was vendor-neutral and what was not
The capstone's governance design uses the factory's gate and guardrail vocabulary
AI-Enabled Project & Delivery Management · GenAI People
31

## Slide 32
DAY 5 · THE ORIGINAL DEPLOYMENT
Case study: one pipeline, four repositories
Repository | Stack | Role in the estate
lighthouse-backend | Python 3.12 · FastAPI · MySQL | Coordination repo — epics filed here
lighthouse-ui | React 19 · Vite · TypeScript | Frontend implementer
lighthouse-sales | FastAPI · Postgres/pgvector · Celery | Sales automation implementer
lighthouse-whatsapp-server | NestJS · Prisma · BullMQ | Messaging implementer
The problem it solved. An agent could write good code, but nothing could tell you where a piece of work was, what it was supposed to do, or who had agreed to it.
What each stage cost, in minutes and in tokens — and where the humans spent their time (mostly at G1, reading specs).
What broke. Cross-repo hand-offs without a shared token; runs that finished green having done nothing; sub-issues stranded with no state after a merge.
What the gates caught. A design that duplicated an existing module; a task ordering that would have shipped a consumer before its schema.
Second case: the same shape on GitHub Copilot
State (issues, labels, milestones, PRs) and content (OpenSpec folders) are vendor-neutral — roughly 70% of the factory did not change
What had to change: how an agent is defined and launched, and how permissions are enforced
Role prompts ported almost verbatim: trigger → mission → numbered steps → guardrails
Discussion for your context: a services engagement with a client PMO, a fixed-price project, a regulated environment — what carries over, what needs a different gate design?
AI-Enabled Project & Delivery Management · GenAI People
32

## Slide 33
DAY 5 · 2 HOURS IN TEAMS OF 3–4, THEN 10-MINUTE PRESENTATIONS
Capstone: an AI-enabled delivery plan for a real release
Brief: a release of 6–8 requirements for a case-study insurance policy-servicing application (teams may substitute a sanitised release of their own). Produce everything with AI; review everything as a team.
1. Release plan
Scope table, sequencing with the dependency that forces it, risks, what to drop, GO / NO-GO — in the Scrum Master's format.
2. Probabilistic forecast
P50 / P85 completion with the assumptions and the two scenarios that move it.
3. Risk register
AI-mined from the requirements and the case history; exposure, owners, early-warning signals.
4. Automation & reporting plan
Which reports and rituals are automated, from which sources, with what human review.
5. Governance design
Which gates exist, who holds them, which are delegated to an agent, which guardrails are controls.
6. Stakeholder pack
A sponsor-grade one-page status and a steering-committee narrative, generated from the plan.
Scored against the six business outcomes: predictability, reporting, risk, automation, governance, AI readiness. Peer critique first, trainer critique second.
AI-Enabled Project & Delivery Management · GenAI People
33

## Slide 34
DAY 5 · CONCLUSION AND CERTIFICATION
Leaving with a plan, not just a certificate
30 days
One report to automate
Pick the report that costs the most hours
Build it from the system of record with an LLM narrator
Run it in parallel with the manual one for two cycles
60 days
One forecast, one gate
Replace a committed date with a P50 / P85
Redesign one sign-off as a real gate with evidence and an approver list
Put an attention queue in front of the sponsor
90 days
One AI-driven initiative
Govern a Gen AI project with evals, budgets and guardrails as controls
Or: factory-enable one sandbox repository and run a first epic
Report what changed in predictability and reporting time
Assessment and certificate
Capstone 60% + scenario-based quiz 40%
Certificate of completion issued on passing; recording and materials retained by the client
Take-home resources
The Software Factory handbook and case studies (open source, MIT)
Prompt library, forecast templates, automation templates, reading list
AI-Enabled Project & Delivery Management · GenAI People
34

## Slide 35
LOGISTICS · ANSWERS TO THE LAB QUESTIONS IN THE REQUEST
Lab setup and system requirements
Hardware (per participant)
Laptop with 8 GB RAM or more
Chrome or Edge, stable internet
Microphone and camera
No GPU; nothing heavy runs locally
Software and accounts
GitHub account (free), added to the sandbox organisation
A Generative AI assistant: Claude, ChatGPT or Microsoft Copilot — the client's enterprise assistant preferred, to respect data policy
Excel or Google Sheets
Teams or Slack sandbox channel
Optional stretch: VS Code, Node.js 20+, Python 3.11+
Provided by the trainer
Sandbox GitHub organisation with the Software Factory installed on a case-study repository
Approver lists configured for the batch
Factory Console deployed for participants
LLM API credits for the factory runs on Days 4–5
Datasets, prompt library, lab guides, templates
Lab cost per participant covers the sandbox environment, the agent-run credits for the labs and capstone, and AI-assistant usage where the client does not supply its own. All required software is available from our side; the client supplies only its own enterprise AI assistant if it prefers one.
AI-Enabled Project & Delivery Management · GenAI People
35

## Slide 36
LOGISTICS · OPTIONAL EXTENSIONS
Delivery format, and topics we can add
Mode | Online, instructor-led, recorded — recording provided to the client
Duration | 20 hours: 5 half-days × 4 hours (4.5 with extended labs)
Batch size | 12–20 participants; capstone in teams of 3–4
Materials | Slide deck, lab guides, prompt library, forecast and automation templates, sandbox estate, the Software Factory handbook
Assessment | Capstone 60% + scenario quiz 40% → certificate of completion
Language | English
Beyond the initial curriculum (60–90 min each, or a sixth half-day)
Agile estimation and planning with AI: story splitting, backlog grooming, sprint-planning assistants
Vendor and contract management for AI-delivered work: acceptance when an agent wrote the code, IP of generated artifacts
Change management and role redesign: BAs, testers and tech leads on an agent-driven pipeline
Portfolio and PMO-level AI: cross-project forecasting, capacity planning, multi-repository estates
Agentic AI deep-dive: event-driven routers versus graph engines, MCP, evaluating agent runs
Build the client's own factory: factory-enable one sandbox repository and run a first epic
AI-Enabled Project & Delivery Management · GenAI People
36

## Slide 37
A plain requirement goes in.
A governed, proven change comes out.
The PM holds the gates.
That is the delivery model this program prepares Project and Delivery Managers to run — and the one they practise, hands-on, for 20 hours.
factory:deployed
Jerry Kurian · GenAI People jerry@genaipeople.com · genaipeople.com · github.com/genai-jerry/claude-software-factory
AI-Enabled Project & Delivery Management · GenAI People
37